## 📊 Overview
EASY DRIVE — LAUNCH TASK TRACKER
Sprint: Apr 7 – May 2, 2026 ¦ Gbemiga Ogele (Technical Lead) & Dayo Ogunniyi (Operations Lead)
COLOUR LEGEND
Gbemiga (Technical) |  | All code, APIs, deployments, testing
Dayo (Operations) |  | Vehicles, legal, insurance, vendors
Shared |  | Both owners must be present / agree
Blocked |  | Cannot start — waiting on a dependency
P0 — Launch Blocker |  | Cannot go live without this done
P1 — Quality |  | Degrades experience but system still works
✅ Complete |  | Mark cell green when task is done
SPRINT SUMMARY
Week | Theme | Key Milestone | Gbemiga Focus | Dayo Focus | Gate Condition | Owner | Status
Week 1 Apr 7–11 | Foundation | Admin can log into live prod site | Supabase + Vercel setup, schema migration, real env vars | Purchase cars, register vehicles, start insurance, order Bouncie GPS | Admin login works on live URL | Both
Week 2 Apr 14–18 | Core Logic | Full E2E flow works in production | Wire PandaDoc, test approval flow, verify GPS & kill switch | Install GPS devices, create PandaDoc template (DUE APR 15) | Test renter applied, approved, Stripe sub created, agreement sent | Both
Week 3 Apr 21–25 | UI & Integration | Both owners sign off on walkthrough | Mobile/browser testing, Stripe live charge, accessibility | Bind insurance, approve SMS templates, prep handoff checklist | Full renter walkthrough passed by both Gbemiga and Dayo | Both
Week 4 Apr 28–May 2 | QA & Launch | First paying renter handed a car | All tests green, security audit, Vercel analytics, launch monitoring | Confirm insurance, FB group posts, vehicle prep, first handoff | First renter paid, signed, and took possession of vehicle | Both
⚠️ CRITICAL DEPENDENCY: Dayo must deliver PandaDoc Template ID to Gbemiga by APR 15. Without this, the approval flow fails and Week 2 cannot complete.

## 🔧 Gbemiga Tasks
EASY DRIVE — GBEMIGA OGELE TASK LIST
Gbemiga Ogele ¦ gbemigaogele@gmail.com ¦ Sprint: Apr 7 – May 2, 2026
Week 1 — Foundation (Apr 7–11)
ID | Priority | Task | Steps to Complete | Due Date | Notes / Dependencies | Status | Done? | Owner
W1-G1 | P0 | Create Supabase production project | 1. Go to supabase.com and sign in 2. Click 'New Project' → name it 'easy-drive-prod' 3. Choose a strong database password and store it in 1Password/notes 4. Wait for project to spin up (~2 min) 5. Go to Settings → API → copy Project URL, anon key, and service_role key 6. Paste all 3 into .env.local replacing the placeholder stub values | Apr 7 |  | Not Started | ☐ | Gbemiga
W1-G2 | P0 | Create Vercel project + connect GitHub repo | 1. Go to vercel.com → New Project 2. Import the easy-drive GitHub repo 3. Set Framework Preset to 'Next.js' 4. Set Root Directory to 'src' (since package.json is inside src/) 5. Do NOT add env vars yet — just confirm it deploys 6. Note the preview URL (e.g. easy-drive-xxx.vercel.app) | Apr 7 | Repo must be on GitHub first | Not Started | ☐ | Gbemiga
W1-G3 | P0 | Replace ALL stub .env.local values with real credentials | 1. Open src/.env.local 2. Replace NEXT_PUBLIC_SUPABASE_URL with real Supabase URL 3. Replace NEXT_PUBLIC_SUPABASE_ANON_KEY with real anon key 4. Replace SUPABASE_SERVICE_ROLE_KEY with real service role key 5. Replace STRIPE_SECRET_KEY with Stripe test secret key (sk_test_...) 6. Replace STRIPE_WEBHOOK_SECRET with placeholder for now (real one after W1-G9) 7. Replace TWILIO_ACCOUNT_SID, TWILIO_AUTH_TOKEN, TWILIO_FROM_NUMBER (Dayo provides number) 8. Replace RESEND_API_KEY from resend.com dashboard 9. Replace PANDADOC_API_KEY from pandadoc.com (Settings → API Keys) 10. Replace BOUNCIE_API_KEY and BOUNCIE_WEBHOOK_SECRET from Bouncie portal | Apr 9 | Dayo provides Twilio number by Apr 14 | Not Started | ☐ | Gbemiga
W1-G4 | P0 | Run DB schema migration to production Supabase | 1. Open terminal in src/ directory 2. Run: npx supabase db push (or npm run supabase:migrate) 3. If prompted, log into Supabase CLI: npx supabase login 4. Link project: npx supabase link --project-ref <your-project-ref> 5. Confirm migration runs without errors 6. Open Supabase dashboard → Table Editor → verify all 9 tables exist: profiles, vehicles, applications, rentals, payments, inspections, maintenance, gps_events, alerts | Apr 8 | Requires W1-G1 complete | Not Started | ☐ | Gbemiga
W1-G5 | P0 | Seed admin accounts in profiles table | 1. Go to Supabase dashboard → Authentication → Users 2. Click 'Invite User' → enter gbemigaogele@gmail.com → send invite 3. Click 'Invite User' → enter day.ogunniyi@gmail.com → send invite 4. Both accept email invites to create Supabase auth accounts 5. Note the UUID of each user from the Authentication → Users table 6. Go to Table Editor → profiles table → Insert row for Gbemiga: auth_user_id=<uuid>, role='admin', full_name='Gbemiga Ogele', email='gbemigaogele@gmail.com' 7. Insert row for Dayo: same fields with Dayo's details and role='admin' 8. Test: go to your live URL /login → send magic link → confirm redirect to /admin | Apr 8 | Requires W1-G4 complete | Not Started | ☐ | Gbemiga
W1-G6 | P0 | Configure Supabase Auth email templates | 1. Go to Supabase dashboard → Authentication → Email Templates 2. Edit 'Magic Link' template — add Easy Drive branding, subject: 'Your Easy Drive sign-in link' 3. Edit 'Invite User' template — used for admin invites 4. Go to Authentication → URL Configuration 5. Set Site URL to your Vercel URL (e.g. https://easy-drive.vercel.app) 6. Add redirect URLs: https://easy-drive.vercel.app/api/auth/callback | Apr 9 |  | Not Started | ☐ | Gbemiga
W1-G7 | P0 | Add all environment variables to Vercel | 1. Go to Vercel project → Settings → Environment Variables 2. Add every variable from src/.env.local one by one 3. Set environment to 'Production' AND 'Preview' for all vars 4. Double-check NEXT_PUBLIC_ vars are prefixed correctly 5. Save all variables | Apr 10 | Requires W1-G3 complete | Not Started | ☐ | Gbemiga
W1-G8 | P0 | Deploy to Vercel production + verify | 1. Trigger a new deploy (push a commit or click 'Redeploy' in Vercel) 2. Wait for build to complete (check build logs for errors) 3. Visit the production URL → confirm landing page loads with full styling 4. Visit /login → confirm magic link form renders 5. Visit /apply → confirm 5-step form renders 6. Send yourself a magic link → confirm email arrives → click link → confirm redirect to /admin | Apr 11 | Requires W1-G5, W1-G7 complete | Not Started | ☐ | Gbemiga
W1-G9 | P0 | Configure Stripe live mode + webhook | 1. Go to stripe.com → Activate your account (fill in business details) 2. Switch dashboard to Live mode (top-left toggle) 3. Go to Developers → API Keys → copy live secret key (sk_live_...) 4. Update STRIPE_SECRET_KEY in Vercel env vars with live key 5. Go to Developers → Webhooks → Add endpoint 6. URL: https://your-domain.vercel.app/api/webhooks/stripe 7. Select events: payment_intent.succeeded, payment_intent.payment_failed, customer.subscription.deleted, invoice.payment_failed 8. Copy Signing Secret → update STRIPE_WEBHOOK_SECRET in Vercel env vars 9. Redeploy Vercel after updating env vars | Apr 10 | Stripe account must be activated with real business info | Not Started | ☐ | Gbemiga
W1-G10 | P0 | Register Bouncie webhook | 1. Log into Bouncie portal (bouncie.com/login) 2. Go to Settings → Webhooks (or API settings) 3. Add webhook URL: https://your-domain.vercel.app/api/webhooks/bouncie 4. Copy the webhook secret → set BOUNCIE_WEBHOOK_SECRET in Vercel env vars 5. Redeploy Vercel after updating env vars | Apr 10 | Requires Dayo to have Bouncie account set up | Not Started | ☐ | Gbemiga
Week 2 — Core Logic (Apr 14–18)
ID | Priority | Task | Steps to Complete | Due Date | Notes / Dependencies | Status | Done? | Owner
W2-G1 | P0 | Test application form → database submission | 1. Open your live site → go to /apply 2. Fill in Step 1 (Personal Info) with test data: name='Test Applicant', phone='+14161234567', email='test@gmail.com' 3. Complete all 5 steps with realistic test data 4. Submit the form 5. Go to Supabase dashboard → Table Editor → applications table 6. Confirm a new row appeared with status='pending' 7. Also check profiles table — confirm a new profile row was created for the test applicant | Apr 14 |  | Not Started | ☐ | Gbemiga
W2-G2 | P0 | Wire PandaDoc template ID into environment | 1. Wait for Dayo to send you the PandaDoc Template ID (DEADLINE: Apr 15) 2. Open Vercel project → Settings → Environment Variables 3. Update PANDADOC_TEMPLATE_ID with the real template ID from Dayo 4. Redeploy Vercel 5. Also update your local .env.local with the same value | Apr 15 | ⚠️ BLOCKED ON DAYO — critical dependency | Not Started | ☐ | Gbemiga
W2-G3 | P0 | Full approval flow end-to-end test in production | 1. Log into /admin with your admin account 2. Find the test application submitted in W2-G1 3. Click Review → Approve 4. Select a vehicle (must have at least one vehicle in fleet table — add one manually via Supabase if needed) 5. Set weekly rate to $300 6. Click 'Approve Application' 7. Confirm: Stripe subscription created (check Stripe dashboard → Subscriptions) 8. Confirm: $500 deposit hold created (check Stripe dashboard → Payment Intents) 9. Confirm: PandaDoc email sent to test applicant email 10. Confirm: SMS sent to test phone number (check Twilio logs) | Apr 16 | Requires W2-G2 complete | Not Started | ☐ | Gbemiga
W2-G4 | P0 | Verify Bouncie GPS events flowing to database | 1. Confirm Dayo has installed GPS devices and registered them in Bouncie portal 2. Ask Dayo to drive one of the cars (or just start the engine) to generate a GPS event 3. Wait 2-3 minutes 4. Go to Supabase → Table Editor → gps_events table 5. Confirm new rows are appearing with lat, lng, speed_kmh, and vehicle_id populated 6. If no events: check Vercel function logs → /api/webhooks/bouncie for errors 7. Common fix: ensure vehicle's bouncie_device_id in vehicles table matches the device IMEI | Apr 15 | ⚠️ BLOCKED ON DAYO — GPS devices must be installed first | Not Started | ☐ | Gbemiga
W2-G5 | P0 | Test geofence breach → admin SMS alert | 1. In Bouncie portal, set a geofence around a specific area 2. Have Dayo drive the test vehicle OUT of that geofence area 3. Confirm geofence exit event appears in gps_events table (geofence_breach = true) 4. Confirm a new row in alerts table with type='geofence_breach', severity='critical' 5. Confirm Gbemiga's phone received an SMS alert from the Twilio number 6. If SMS not received: check Twilio logs → check TWILIO_FROM_NUMBER env var is set | Apr 17 | Requires W2-G4 and Bouncie geofence configured | Not Started | ☐ | Gbemiga
W2-G6 | P0 | Kill switch integration test on real vehicle | 1. Ensure one test vehicle has a Bouncie device installed and is in a safe location (parked, engine running) 2. Log into /admin → go to Rentals → find the active rental for that vehicle 3. Open Kill Switch panel → enter reason: 'Integration test - authorized by both owners' 4. Click 'Disable Ignition' → confirm the modal → click confirm 5. Dayo confirms in the car that the engine cuts (or starter is disabled) 6. Check alerts table: confirm kill switch audit log entry created 7. Re-enable ignition via admin panel 8. Confirm vehicle starts again | Apr 18 | ⚠️ BLOCKED ON DAYO — requires real vehicle with Bouncie installed | Not Started | ☐ | Gbemiga
W2-G7 | P0 | Test payment failure webhook | 1. In Stripe test mode, use card number 4000 0000 0000 0341 (always declines) 2. Trigger a payment failure via the Stripe dashboard (create a payment intent and confirm with that card) 3. Or: use Stripe CLI: stripe trigger payment_intent.payment_failed 4. Check Supabase → alerts table: confirm new row with type='payment_failed' 5. Confirm SMS sent to renter's phone from Twilio (check Twilio message logs) 6. If nothing fires: check Vercel logs → /api/webhooks/stripe | Apr 17 | Use Stripe CLI: npm install -g stripe for easier testing | Not Started | ☐ | Gbemiga
Week 3 — UI & Integration (Apr 21–25)
ID | Priority | Task | Steps to Complete | Due Date | Notes / Dependencies | Status | Done? | Owner
W3-G1 | P0 | Mobile test — apply form on real device | 1. Open your live URL on an iPhone or Android phone (NOT browser dev tools) 2. Go to /apply → complete each of the 5 steps 3. On Step 4 (Documents): tap the camera icon → confirm device camera opens 4. Check all form fields are large enough to tap easily (min 44px height) 5. Check no text overflows or wraps oddly on 375px width 6. Test in both portrait and landscape orientation 7. Submit the form → confirm confirmation page renders correctly | Apr 21 | Use a real phone, not browser DevTools mobile emulation | Not Started | ☐ | Gbemiga
W3-G2 | P0 | Cross-browser testing | 1. Test on Safari (macOS or iPhone) — most likely to have CSS bugs 2. Test on Firefox (Windows or Mac) 3. Test on Chrome (baseline — should already work) 4. For each browser: check landing page, /login, /apply form, /admin dashboard 5. Fix any layout breaks (Safari especially: sticky positioning, backdrop-blur, gap) 6. Re-test after fixes | Apr 22 | Pay special attention to Safari — it handles CSS differently | Not Started | ☐ | Gbemiga
W3-G3 | P0 | Add WhatsApp number to codebase | 1. Receive WhatsApp Business number from Dayo (should be done by Apr 14) 2. Open src/app/(public)/page.tsx 3. Find the WhatsApp float button (bottom of file) 4. Replace the placeholder href with: https://wa.me/1XXXXXXXXXX (replace with real number in E.164 format without +) 5. Find the WhatsApp link in the footer section 6. Replace there too 7. Commit and deploy to Vercel 8. Test: click the float button on mobile → confirm WhatsApp opens with the correct number | Apr 21 | ⚠️ BLOCKED ON DAYO — needs WhatsApp number by Apr 14 | Not Started | ☐ | Gbemiga
W3-G4 | P1 | Set up Resend custom domain for branded email | 1. Log into resend.com → Domains → Add Domain 2. Enter your domain (e.g. easydrive.ca) 3. Resend will show DNS records to add (TXT, MX, DKIM) 4. Add those DNS records in your domain registrar (GoDaddy, Namecheap, etc.) 5. Wait for DNS propagation (15 min to 2 hours) 6. Verify the domain in Resend dashboard 7. Update RESEND_FROM_EMAIL in Vercel env vars to hello@easydrive.ca 8. Redeploy and send a test email to confirm it arrives from the branded address | Apr 22 | Requires domain (easydrive.ca) to be purchased and DNS access | Not Started | ☐ | Gbemiga
W3-G5 | P0 | Accessibility audit — keyboard navigation | 1. Open the live site → press Tab key to navigate through the landing page 2. Every clickable element must have a visible focus ring (blue or teal outline) 3. Tab through /apply form: all inputs, buttons, file uploads must be reachable by keyboard 4. Open admin /admin/applications → tab through all interactive elements 5. Open screen reader (Windows: Win+Ctrl+Enter for Narrator, Mac: Cmd+F5 for VoiceOver) 6. Navigate apply form with screen reader — all labels must be read aloud correctly 7. Fix any missing aria-label, aria-describedby, or unlabelled inputs found | Apr 23 |  | Not Started | ☐ | Gbemiga
W3-G6 | P0 | Stripe live mode end-to-end charge | 1. Switch Stripe dashboard to LIVE mode 2. Ensure STRIPE_SECRET_KEY in Vercel is the live key (sk_live_...) 3. Go through the full payment setup flow: submit application → approve → payment setup 4. Use your own real credit card to create a $1 test charge 5. Confirm charge appears in Stripe live dashboard 6. Immediately refund: go to Stripe → Payments → find the charge → Refund 7. Confirm refund processed 8. This proves the live payment flow works before real renters use it | Apr 25 | Use your own card — refund immediately after. Document the test. | Not Started | ☐ | Gbemiga
W3-G7 | P0 | Update landing page pricing for launch reality | 1. Open src/app/(public)/page.tsx 2. Find the 3 pricing cards (Economy, Mid-size, Hybrid) 3. Keep Economy card as-is 4. Add 'Coming Soon' badge to Mid-size card and grey out the Apply button 5. Add 'Coming Soon' badge to Hybrid card and grey out the Apply button 6. Confirm with Dayo what vehicle(s) were purchased — update Economy card vehicle examples if needed 7. Commit and deploy | Apr 21 | ⚠️ Confirm vehicle model with Dayo before updating | Not Started | ☐ | Gbemiga
Week 4 — QA & Launch (Apr 28 – May 2)
ID | Priority | Task | Steps to Complete | Due Date | Notes / Dependencies | Status | Done? | Owner
W4-G1 | P0 | Run full Vitest test suite | 1. Open terminal in src/ directory 2. Run: npm test 3. All 41 tests must pass (4 test files: sanitize, application, stripe, webhooks) 4. If any tests fail: fix the underlying code, do not delete the test 5. Run again to confirm green 6. Run: npm run typecheck → zero TypeScript errors 7. Run: npm run lint → zero ESLint warnings | Apr 28 |  | Not Started | ☐ | Gbemiga
W4-G2 | P0 | Security audit | 1. Test 1 — RLS: Log in as a renter account. Try to access /admin in the browser → must redirect to /portal 2. Test 2 — RLS: Using Postman or curl, call GET /api/applications with a renter JWT → must return 403 3. Test 3 — Kill switch auth: Call POST /api/rentals/<id>/killswitch with a renter JWT → must return 403 4. Test 4 — HMAC: Send a POST to /api/webhooks/stripe with a fake body and wrong signature → must return 400 5. Test 5 — HMAC: Same for /api/webhooks/bouncie 6. Test 6 — XSS: Enter <script>alert(1)</script> into the apply form → confirm it is sanitized in the DB (no HTML stored) 7. Document each test result | Apr 29 | Document all results — this is your security sign-off | Not Started | ☐ | Gbemiga
W4-G3 | P1 | Set up Vercel Analytics and error monitoring | 1. In Vercel project dashboard → Analytics tab → Enable Analytics (free) 2. Go to vercel.com/integrations → find Sentry → install (free tier is sufficient) 3. Or: go to vercel.com project → Settings → Integrations → Log Drains 4. After setup: trigger a deliberate error (visit a non-existent page) → confirm it surfaces in the monitoring tool 5. Set up email alert in Sentry for any new error type | Apr 29 |  | Not Started | ☐ | Gbemiga
W4-G4 | P0 | Verify custom domain and SSL | 1. Go to Vercel project → Settings → Domains 2. Add your domain: easydrive.ca 3. In your domain registrar, add the Vercel A record or CNAME shown 4. Wait for DNS propagation (can take up to 24 hours) 5. Confirm https://easydrive.ca loads the landing page 6. Confirm the padlock (SSL) shows in browser — certificate auto-issued by Vercel | Apr 28 | Start DNS propagation early — it can take hours | Not Started | ☐ | Gbemiga
W4-G5 | P0 | Monitor first day of real traffic | 1. Keep Vercel dashboard open in a browser tab 2. Monitor Functions tab for any 500 errors in real-time 3. Monitor Supabase dashboard → Logs for any DB errors 4. Keep Stripe dashboard open → monitor for any failed webhook events 5. Have Twilio dashboard open → confirm SMS messages are delivering 6. Log all issues in a running notes document, prioritize and fix P0 bugs same day | May 1 | Be available on your phone all day on launch day | Not Started | ☐ | Gbemiga

## 🚗 Dayo Tasks
EASY DRIVE — DAYO OGUNNIYI TASK LIST
Dayo Ogunniyi ¦ day.ogunniyi@gmail.com ¦ Sprint: Apr 7 – May 2, 2026
Week 1 — Foundation (Apr 7–11)
ID | Priority | Task | Steps to Complete | Due Date | Notes / Dependencies | Status | Done? | Owner
W1-D1 | P0 | Register 'Easy Drive' trade name — Ontario Business Registry | 1. Go to ontario.ca/page/ontario-business-registry 2. Sign in with your ONe-key account (or create one) 3. Click 'Register a Business Name' 4. Enter trade name: Easy Drive 5. Select GB Trade and Logistics Inc. as the registering entity 6. Pay the ~$60 fee by credit card 7. Download and save the registration certificate — Gbemiga needs a copy for legal records 8. This is required before you can advertise the business publicly | Apr 7 | Do this FIRST on Day 1 — everything else flows from this | Not Started | ☐ | Dayo
W1-D2 | P0 | Apply for GTA municipal business license | 1. Identify your operating municipality (Toronto, Mississauga, Brampton, etc.) 2. Toronto: toronto.ca/services-payments/permits-licences-bylaws → search 'vehicle rental' 3. Mississauga: mississauga.ca/en/business/licences-and-permits → search 'vehicle rental' 4. Gather required documents: proof of business registration, insurance (when available), photo ID 5. Submit the application — fee ~$150–$300 6. Note the expected processing time (may be 2–6 weeks) 7. Request a receipt/confirmation number 8. NOTE: You can operate in soft launch (friends/family) while application is processing | Apr 8 | Processing takes 2–6 weeks — apply NOW even before vehicles are purchased | Not Started | ☐ | Dayo
W1-D3 | P0 | Purchase Vehicle #1 — Economy tier | 1. Target: Toyota Corolla, Honda Civic, Hyundai Elantra (2015–2020 preferred) 2. Budget: $4,000–$6,000 CAD 3. Sources: Facebook Marketplace (search 'GTA cars under 6000'), Copart.com, ADESA auction 4. Key checks before purchase: Carfax report (carfax.ca), Ontario Safety Certificate status, rust inspection underneath, no active liens (search at ServiceOntario) 5. Mileage guideline: under 200,000 km preferred for rental reliability 6. Negotiate — most FB Marketplace sellers accept 10–15% below asking 7. Get a signed bill of sale with the seller's full name, address, and vehicle VIN 8. Do NOT register the car in your personal name — use GB Trade and Logistics Inc. on all paperwork | Apr 9 | Have a mechanic friend inspect before buying if possible | Not Started | ☐ | Dayo
W1-D4 | P0 | Purchase Vehicle #2 — Economy tier | 1. Same criteria as Vehicle #1 2. Try to match makes/models for easier insurance and maintenance (e.g. two Corollas) 3. Keep purchase receipts for both cars — needed for insurance, accounting, and tax 4. Both vehicles go on the business asset register under GB Trade and Logistics Inc. | Apr 9 |  | Not Started | ☐ | Dayo
W1-D5 | P0 | Register both vehicles with RIN + obtain Ontario plates | 1. Bring to ServiceOntario: bill of sale, your RIN number, proof of insurance (when bound), photo ID 2. Register each vehicle to GB Trade and Logistics Inc. using the RIN 3. Plates stay with the vehicle in Ontario — you own and manage them 4. Note the plate number and VIN of each car → send both to Gbemiga for the fleet database 5. Note the plate renewal dates → Gbemiga will enter these in the system for expiry warnings | Apr 10 | ⚠️ Insurance must be bound before you can plate the vehicle | Not Started | ☐ | Dayo
W1-D6 | P0 | Get commercial auto insurance quotes | 1. Call or email at least 3 brokers — do NOT use personal auto insurance 2. Tell them: 'commercial vehicle rental, 2 cars, used for gig delivery by renters' 3. Recommended brokers to contact: Intact Insurance, Aviva Canada, Economical Insurance, Gore Mutual 4. Ask specifically for: non-owned auto coverage + commercial rental fleet policy 5. Budget ~$200–$400/month for 2 vehicles (commercial rental is expensive) 6. Get quotes in writing 7. Target binding (signing) the policy by Apr 23 8. Once bound: get Certificate of Insurance → needed for vehicle plating and first rental | Apr 9 | Start quotes immediately — binding can take 3–10 business days | Not Started | ☐ | Dayo
W1-D7 | P0 | Order 2 Bouncie GPS units | 1. Go to bouncie.com 2. Add 2x Bouncie Trip + GPS tracker to cart (~$67 CAD each) 3. Choose Express shipping to arrive by Apr 14 4. Create a Bouncie account with your email (day.ogunniyi@gmail.com) 5. Note: the monthly fee is $8 USD per device 6. Once delivered: send Gbemiga the Bouncie account email so he can register the webhook | Apr 8 | Order with Express shipping — must arrive before Apr 14 | Not Started | ☐ | Dayo
W1-D8 | P0 | Set up Easy Drive bank account + HST tracking | 1. Open a business chequing account in GB Trade and Logistics Inc. name (or a separate sub-account) 2. Suggested banks: RBC, TD, or Scotiabank business banking 3. All rental income must flow through this account for clean bookkeeping 4. Contact your accountant: all weekly rental fees ($300–$450) are subject to HST (15%) — confirm collection and remittance process 5. Set up a simple spreadsheet to track: rental income per week, HST collected, vehicle expenses | Apr 11 |  | Not Started | ☐ | Dayo
Week 2 — Core Logic (Apr 14–18)
ID | Priority | Task | Steps to Complete | Due Date | Notes / Dependencies | Status | Done? | Owner
W2-D1 | P0 | Install Bouncie GPS unit in Vehicle #1 | 1. Locate the OBD-II port in the car — it is under the dashboard on the driver's side (usually near the steering column) 2. Plug the Bouncie device firmly into the OBD-II port 3. Open the Bouncie app on your phone → Add Vehicle → follow on-screen instructions 4. Enter vehicle details: make, model, year, VIN 5. Note the device IMEI number (on the device label or in the Bouncie app) 6. Send IMEI to Gbemiga so he can enter it as bouncie_device_id in the vehicles table 7. Take the car for a 5-minute drive → confirm trip appears in Bouncie app | Apr 14 | ⚠️ CRITICAL — Gbemiga cannot test GPS features until this is done | Not Started | ☐ | Dayo
W2-D2 | P0 | Install Bouncie GPS unit in Vehicle #2 | 1. Same process as Vehicle #1 2. Send the IMEI for Vehicle #2 to Gbemiga 3. Drive to confirm trip tracking works in Bouncie app | Apr 14 |  | Not Started | ☐ | Dayo
W2-D3 | P0 | Purchase Canadian Twilio phone number | 1. Go to twilio.com/console → log in (Gbemiga likely set up the account — confirm with him) 2. Go to Phone Numbers → Buy a Number 3. Country: Canada, Area code: 416 or 647 (Toronto) 4. Ensure the number has SMS capability 5. Purchase the number (~$1.15 CAD/month) 6. Send the phone number to Gbemiga for the TWILIO_FROM_NUMBER env var | Apr 14 |  | Not Started | ☐ | Dayo
W2-D4 | P0 | Set up WhatsApp Business + provide number to Gbemiga | 1. Download WhatsApp Business app on your phone 2. Set up with the Easy Drive phone number (could be the Twilio number or a dedicated line) 3. Business name: Easy Drive, Category: Automotive 4. Set away message: 'Thanks for reaching out to Easy Drive! We typically respond within 2 hours. For faster answers visit easydrive.ca' 5. Send the WhatsApp number to Gbemiga — he will add it to the website | Apr 14 | ⚠️ HARD DEADLINE — Gbemiga needs this to update the website | Not Started | ☐ | Dayo
W2-D5 | P0 | CREATE PANDADOC RENTAL AGREEMENT TEMPLATE — HARD DEADLINE APR 15 | 1. Go to pandadoc.com → sign in (or create account with day.ogunniyi@gmail.com) 2. Go to Templates → New Template → Start from scratch 3. Template must include ALL of the following sections: 4. (a) Parties: Lessor (GB Trade and Logistics Inc. o/a Easy Drive) and Renter (name field) 5. (b) Vehicle details: Make, Model, Year, VIN, Plate (fill-in fields) 6. (c) Rental period: Start date, weekly rate, auto-renewal terms 7. (d) Deposit: $500 refundable deposit terms, conditions for deductions 8. (e) Payment terms: weekly in advance, pre-authorized 9. (f) GPS + Kill Switch Disclosure: 'Renter acknowledges the vehicle is equipped with a GPS tracking device and remote ignition interrupt (kill switch). This may be activated in cases of: non-payment, geofence breach, stolen vehicle, or breach of rental terms.' 10. (g) Permitted use: Ontario only, gig delivery platforms only 11. (h) Insurance: renter responsible for personal injury; vehicle covered by lessor's commercial policy 12. (i) Return conditions and inspection process 13. (j) Early termination: 72-hour written notice required 14. (k) Signature fields for both renter and GB Trade and Logistics Inc. representative 15. Once template is saved: go to Templates → click the template → copy the Template ID from the URL (it looks like: abc123xyz) 16. Send the Template ID to Gbemiga IMMEDIATELY 17. Send Gbemiga your PandaDoc API key (Settings → API Keys → copy) | Apr 15 | ⚠️ HARDEST DEADLINE IN THE PROJECT — everything stops without this | Not Started | ☐ | Dayo
W2-D6 | P0 | Paralegal review of rental agreement | 1. Engage a paralegal (NOT a full lawyer — cheaper, ~$200–$400 for 1 hour) 2. Find one at: paralegalscope.ca or lsrs.lso.ca (Law Society Referral Service) 3. Share the PandaDoc template with the paralegal 4. Ask them to review specifically: (1) Ontario Consumer Protection Act compliance, (2) kill switch disclosure and consent language, (3) deposit terms, (4) liability language 5. Get written sign-off (even a short email saying 'reviewed and approved') 6. Make any changes they recommend in the PandaDoc template 7. If they request changes: update the template and notify Gbemiga of any change to the Template ID | Apr 16 |  | Not Started | ☐ | Dayo
W2-D7 | P0 | Join GTA gig driver Facebook groups (listening phase) | 1. Join: 'GTA Uber Eats Drivers' group on Facebook 2. Join: 'DoorDash Drivers Toronto / GTA' group 3. Join: 'SkipTheDishes Ontario Drivers' group 4. Join: 'Gig Workers Canada' group 5. Do NOT post ads yet — just observe, learn the language, understand pain points 6. Note any posts asking about vehicle rentals — this is your target market 7. This research will make your Week 4 launch posts much more effective | Apr 14 | Listening only this week — post in Week 4 after site is confirmed live | Not Started | ☐ | Dayo
Week 3 — UI & Integration (Apr 21–25)
ID | Priority | Task | Steps to Complete | Due Date | Notes / Dependencies | Status | Done? | Owner
W3-D1 | P0 | Bind commercial insurance policy | 1. Follow up with all 3 insurance brokers from Week 1 2. Select the best quote (balance of coverage and cost) 3. Provide broker with: vehicle VINs, plate numbers, business registration certificate, purpose of use (commercial rental for gig drivers) 4. Sign the policy documents 5. Obtain the Certificate of Insurance (pink card equivalent for commercial) 6. Send a copy to Gbemiga for records 7. NOTE: Do not hand any vehicle to a renter before this is bound. This is not negotiable. | Apr 23 | ⚠️ NO INSURANCE = NO RENTAL. Hard stop. | Not Started | ☐ | Dayo
W3-D2 | P0 | Full website walkthrough as a real renter | 1. Use your personal phone (not admin account) 2. Go to easydrive.ca → browse the landing page as if you are a gig driver seeing it for the first time 3. Click Apply → fill in all 5 steps with realistic test data 4. Note anything that is confusing, unclear, or broken 5. Submit the application 6. Log in with your admin account → go to /admin/applications → find your test application 7. Go through the review and approve process 8. Document all issues in a list and send to Gbemiga 9. Sign off only when you can complete the process without confusion | Apr 22 | Be a harsh critic — this is the experience your first real renter will have | Not Started | ☐ | Dayo
W3-D3 | P1 | Review and approve all SMS notification templates | 1. Ask Gbemiga to send you copies of all 5 SMS templates 2. Review each for tone, clarity, and accuracy: 3. (1) Approval SMS: 'Your Easy Drive application has been approved! Please check your email for next steps.' 4. (2) Rejection SMS: 'Unfortunately your Easy Drive application was not approved at this time. Questions? WhatsApp us at XXX-XXX-XXXX' 5. (3) Payment reminder: 'Easy Drive: Your weekly payment of $XXX is due tomorrow. Questions? Reply to this message.' 6. (4) Geofence breach (to admin): 'ALERT: Vehicle PLATE-XXX has left the approved zone. Check admin dashboard immediately.' 7. (5) Kill switch: 'Easy Drive: Your vehicle's ignition has been disabled. Contact us immediately at XXX-XXX-XXXX to resolve.' 8. Approve or request edits — this is your customer voice, it must be right | Apr 23 |  | Not Started | ☐ | Dayo
W3-D4 | P0 | Create vehicle handoff checklist (physical document) | 1. Create a 1-page printed checklist for the moment a renter picks up a car 2. Must include: Date/time of handoff, Renter full name + photo ID verified checkbox, Vehicle make/model/year/plate, Odometer reading at pickup, Fuel level (full/3/4/half/quarter), Condition notes (any pre-existing scratches/dents — note them explicitly), Photo checklist (front, rear, driver side, passenger side, interior — all taken), PandaDoc agreement status: signed? (confirm in admin panel before handing keys), Renter phone number confirmed, Renter shown how to report issues (WhatsApp number), Both signatures: renter + you 3. Print 10 copies before Week 4 | Apr 24 |  | Not Started | ☐ | Dayo
W3-D5 | P0 | Final content review of entire website | 1. Go through every page: landing, login, apply, submitted confirmation 2. Check pricing: does it match what you are actually charging? ($300–$330 Economy) 3. Check FAQ: are all answers accurate for YOUR business (Ontario rules, deposit, etc.)? 4. Check trust signals: are all the claims (unlimited mileage, no hard check, etc.) things you can deliver? 5. Check footer: does it have Easy Drive trade name, GB Trade and Logistics Inc., correct contact info? 6. Make a list of all corrections → send to Gbemiga by Apr 25 for final update | Apr 25 | You are the operations expert — this sign-off is yours to own | Not Started | ☐ | Dayo
W3-D6 | P0 | Safety certificate check on both vehicles | 1. Ontario law requires a valid Safety Standards Certificate at the point of rental 2. If either vehicle does not have a current safety cert (valid 36 days from issue): book it into a licensed mechanic for a safety inspection 3. Cost: ~$100–$150 per vehicle 4. File the certificates and note the expiry dates → send to Gbemiga for fleet expiry warnings in the system 5. A vehicle CANNOT be rented without a valid safety cert | Apr 24 | ⚠️ Legal requirement — no cert, no rental | Not Started | ☐ | Dayo
Week 4 — QA & Launch (Apr 28 – May 2)
ID | Priority | Task | Steps to Complete | Due Date | Notes / Dependencies | Status | Done? | Owner
W4-D1 | P0 | Confirm insurance certificate received and filed | 1. Ensure the commercial insurance policy is bound (signed and active) 2. Receive the Certificate of Insurance (CoI) from your broker 3. Keep a digital copy (scan or photo) and a physical copy in each vehicle's glovebox 4. Send a copy to Gbemiga 5. Confirm with broker: does the policy cover the vehicle during the rental period when a renter is driving? (It must.) | Apr 28 | ⚠️ NO INSURANCE = NO RENTAL. Absolute requirement. | Not Started | ☐ | Dayo
W4-D2 | P0 | Prepare both vehicles for first rental | 1. Clean both vehicles inside and out (professional clean recommended — first impression matters) 2. Fill both tanks to full 3. Check tire pressure on all 4 tires (under-inflated tires = renter complaint) 4. Ensure Bouncie GPS device is firmly plugged in and showing online in the app 5. Take final pre-rental condition photos of both cars (timestamp them) 6. Place a printed copy of the handoff checklist in the glovebox 7. Place a business card or note with Easy Drive WhatsApp number in the glovebox 8. Confirm safety certificate is in the glovebox | Apr 30 |  | Not Started | ☐ | Dayo
W4-D3 | P0 | Write and post Facebook group launch posts | 1. WAIT for Gbemiga to confirm the site is live and all tests are green before posting 2. Write 3 different posts — one per Facebook group — each slightly different tone 3. Do NOT sound like an ad. Sound like a person sharing a service they built: 4. Example post: 'Hey everyone — I built a weekly car rental service specifically for GTA gig drivers. No hard credit check, GPS-tracked, commercially insured, unlimited mileage. Starting at $300/week. First 2 spots available now. DM me or WhatsApp [number].' 5. Post in: GTA Uber Eats Drivers, DoorDash Drivers Toronto, and one other group 6. Respond to EVERY comment and message within 2 hours on launch day | Apr 30 | ⚠️ ONLY post after Gbemiga confirms system is stable | Not Started | ☐ | Dayo
W4-D4 | P0 | Conduct first vehicle handoff | 1. Before handing keys: log into admin panel (or call Gbemiga) to confirm PandaDoc agreement shows 'signed' status 2. Check Stripe shows the subscription is active and deposit hold is in place 3. If both confirmed: proceed with handoff 4. Use the printed handoff checklist — complete every item 5. Take timestamped condition photos: front, rear, both sides, interior 6. Record odometer 7. Walk the renter through the vehicle: how to report issues, WhatsApp number, no driving outside Ontario 8. Both sign the handoff checklist 9. Hand over the keys 10. Immediately text Gbemiga: 'First rental live — [name], [vehicle plate], [start date]' | May 1 | This is the moment the business becomes real. Do it right. | Not Started | ☐ | Dayo
W4-D5 | P0 | Monitor admin dashboard daily — first week operations | 1. Log into easydrive.ca/admin every morning 2. Check Alerts panel: any geofence breaches, payment failures, or system alerts? 3. Check Applications: respond to new applicants within 24 hours 4. Check GPS last seen for each active vehicle: does it match where the renter said they would be? 5. Escalate IMMEDIATELY to Gbemiga: any 'critical' severity alert 6. Escalate IMMEDIATELY to Gbemiga: any alert you do not understand or cannot resolve yourself 7. Keep a daily log: date, what you saw, what you did | May 1–7 | You are the operational eyes on the system every day | Not Started | ☐ | Dayo
W4-D6 | P1 | Collect first renter feedback after 48 hours | 1. After 48 hours of the first rental, send a WhatsApp message to the renter 2. Message: 'Hey [name], Dayo here from Easy Drive. How has the car been so far? Anything we can improve with the pickup process?' 3. Write down exactly what they say — even if it is negative 4. Bring all feedback to the Week 4 retrospective with Gbemiga 5. This is your first product insight. It will shape Phase 2. | May 3 |  | Not Started | ☐ | Dayo

## ⚠️ Dependencies
BLOCKED TASKS & DEPENDENCY TRACKER
These tasks CANNOT start until their dependency is resolved. Track status here daily.
Blocked Task ID | Blocked Task | Blocked Owner | Depends On | Providing Owner | Deadline | Status
W2-G2 | Wire PandaDoc template ID into env vars | Gbemiga | W2-D5: Dayo creates PandaDoc template + provides template ID | Dayo | APR 15 ‼️ | Waiting
W3-G3 | Add WhatsApp number to website | Gbemiga | W2-D4: Dayo sets up WhatsApp Business + provides number | Dayo | Apr 14 | Waiting
W2-G4 | Verify Bouncie GPS events in database | Gbemiga | W2-D1 + W2-D2: Dayo installs GPS devices in both vehicles | Dayo | Apr 15 | Waiting
W2-G6 | Kill switch integration test | Both | W2-D1: GPS installed + vehicle purchased + both available | Dayo | Apr 18 | Waiting
W1-G5 | Seed admin accounts | Gbemiga | Both Gbemiga and Dayo accept Supabase auth invites via email | Both | Apr 8 | Waiting
W4-D3 | Post Facebook group launch announcements | Dayo | W4-G1: Gbemiga confirms all tests green + site stable | Gbemiga | Apr 30 | Waiting
W4-D4 | First vehicle handoff | Dayo | W3-D1: Insurance bound + W2-G3: PandaDoc signed by renter | Both | May 1 | Waiting
W1-D5 | Register vehicles + get plates | Dayo | W1-D6: Insurance quote started (needed for plating) | Dayo | Apr 10 | Waiting

## 📅 Milestone Calendar
EASY DRIVE — 4-WEEK LAUNCH CALENDAR
Date | Week / Phase | Milestone / Event | Owner | Priority | Status
Apr 7 (Mon) | Week 1 — Foundation | Register 'Easy Drive' trade name at Ontario Business Registry | Dayo | P0 | Pending
Apr 7 (Mon) | Week 1 — Foundation | Create Supabase prod project + Vercel project | Gbemiga | P0 | Pending
Apr 8 (Tue) | Week 1 — Foundation | Apply for GTA municipal business license | Dayo | P0 | Pending
Apr 8 (Tue) | Week 1 — Foundation | Run database schema migration to production | Gbemiga | P0 | Pending
Apr 8 (Tue) | Week 1 — Foundation | Seed admin accounts (Gbemiga + Dayo) | Gbemiga | P0 | Pending
Apr 9 (Wed) | Week 1 — Foundation | Purchase Vehicle #1 and Vehicle #2 | Dayo | P0 | Pending
Apr 9 (Wed) | Week 1 — Foundation | Start commercial insurance quotes (3 brokers minimum) | Dayo | P0 | Pending
Apr 9 (Wed) | Week 1 — Foundation | Order Bouncie GPS units (Express shipping) | Dayo | P0 | Pending
Apr 9 (Wed) | Week 1 — Foundation | Replace all .env.local stubs with real credentials | Gbemiga | P0 | Pending
Apr 10 (Thu) | Week 1 — Foundation | Configure Stripe live mode + register webhook endpoint | Gbemiga | P0 | Pending
Apr 10 (Thu) | Week 1 — Foundation | Register vehicles with RIN + get Ontario plates | Dayo | P0 | Pending
Apr 11 (Fri) | Week 1 — Foundation | 🏁 GATE 1: Admin login confirmed on live prod URL | Both | P0 | Pending
Apr 14 (Mon) | Week 2 — Core Logic | Install Bouncie GPS in Vehicle #1 + Vehicle #2 | Dayo | P0 | Pending
Apr 14 (Mon) | Week 2 — Core Logic | Purchase Canadian Twilio phone number | Dayo | P0 | Pending
Apr 14 (Mon) | Week 2 — Core Logic | Set up WhatsApp Business + send number to Gbemiga | Dayo | P0 | Pending
Apr 14 (Mon) | Week 2 — Core Logic | Test application form → confirm data in Supabase | Gbemiga | P0 | Pending
⚠️ APR 15 | Week 2 — Core Logic | ⚠️ HARD DEADLINE: Dayo sends PandaDoc template ID to Gbemiga | Dayo | P0 | Pending
Apr 15 (Tue) | Week 2 — Core Logic | Wire PandaDoc template ID into Vercel env vars + redeploy | Gbemiga | P0 | Pending
Apr 15 (Tue) | Week 2 — Core Logic | Verify Bouncie GPS events flowing into gps_events table | Gbemiga | P0 | Pending
Apr 16 (Wed) | Week 2 — Core Logic | Full approval flow E2E test: apply → approve → Stripe + PandaDoc | Gbemiga | P0 | Pending
Apr 16 (Wed) | Week 2 — Core Logic | Paralegal review of rental agreement | Dayo | P0 | Pending
Apr 17 (Thu) | Week 2 — Core Logic | Test geofence breach → admin SMS alert fires | Gbemiga | P0 | Pending
Apr 18 (Fri) | Week 2 — Core Logic | Kill switch live test on real vehicle — both owners present | Both | P0 | Pending
Apr 18 (Fri) | Week 2 — Core Logic | 🏁 GATE 2: Full E2E flow proven in production | Both | P0 | Pending
Apr 21 (Mon) | Week 3 — UI & Integration | Mobile test apply form on real iPhone/Android | Gbemiga | P0 | Pending
Apr 21 (Mon) | Week 3 — UI & Integration | Update pricing cards (Economy only, others Coming Soon) | Gbemiga | P0 | Pending
Apr 22 (Tue) | Week 3 — UI & Integration | Cross-browser test (Safari, Firefox, Chrome) | Gbemiga | P0 | Pending
Apr 22 (Tue) | Week 3 — UI & Integration | Full renter walkthrough by Dayo — report UX issues | Dayo | P0 | Pending
Apr 23 (Wed) | Week 3 — UI & Integration | Bind commercial insurance policy | Dayo | P0 | Pending
Apr 23 (Wed) | Week 3 — UI & Integration | Accessibility audit — keyboard + screen reader | Gbemiga | P0 | Pending
Apr 24 (Thu) | Week 3 — UI & Integration | Safety certificates verified on both vehicles | Dayo | P0 | Pending
Apr 24 (Thu) | Week 3 — UI & Integration | Vehicle handoff checklist printed (10 copies) | Dayo | P1 | Pending
Apr 25 (Fri) | Week 3 — UI & Integration | Stripe live mode end-to-end charge + refund | Gbemiga | P0 | Pending
Apr 25 (Fri) | Week 3 — UI & Integration | Final content review sign-off by Dayo | Dayo | P0 | Pending
Apr 25 (Fri) | Week 3 — UI & Integration | 🏁 GATE 3: Both owners walkthrough signed off | Both | P0 | Pending
Apr 28 (Mon) | Week 4 — Launch | npm test: all 41 unit tests green | Gbemiga | P0 | Pending
Apr 28 (Mon) | Week 4 — Launch | Custom domain (easydrive.ca) pointed to Vercel + SSL active | Gbemiga | P0 | Pending
Apr 28 (Mon) | Week 4 — Launch | Confirm insurance certificate filed and vehicles ready | Dayo | P0 | Pending
Apr 29 (Tue) | Week 4 — Launch | Security audit: RLS bypass, HMAC bypass, XSS tests | Gbemiga | P0 | Pending
Apr 29 (Tue) | Week 4 — Launch | Set up Vercel Analytics + error monitoring | Gbemiga | P1 | Pending
Apr 30 (Wed) | Week 4 — Launch | Bug fix sprint (issues from Gate 3 walkthrough) | Gbemiga | P0 | Pending
Apr 30 (Wed) | Week 4 — Launch | Vehicles cleaned, fueled, GPS confirmed active | Dayo | P0 | Pending
Apr 30 (Wed) | Week 4 — Launch | 🚀 Post Facebook group soft launch announcements (after Gbemiga confirms stable) | Dayo | P0 | Pending
May 1 (Thu) | Week 4 — Launch | 🎉 FIRST VEHICLE HANDOFF — first paying renter | Dayo | P0 | Pending
May 1 (Thu) | Week 4 — Launch | Monitor Vercel logs, Supabase logs, Stripe — all day | Gbemiga | P0 | Pending
May 2 (Fri) | Week 4 — Launch | Verify first Stripe weekly charge fires correctly | Gbemiga | P0 | Pending
May 2 (Fri) | Week 4 — Launch | 🏁 GATE 4 = LAUNCH: First renter paid, signed, has the car | Both | P0 | Pending